## Sheet1
ID | User Story | Sprint Number | Story Priority | Story Status | Story Points
13 | As someone who owns a small business, I want an app that tracks my progress being productive, so I can track and be proactive with a self-set schedule. | 1,2,3,4 &5 | 1 | IP | 4
1 | As a professional, I would like calendar functionality so that I may keep my schedule organized. | 1,2,3,4 &5 | 2 | IP | 5
7 | As a user, I want to be able to login through my existing accounts (Google) so I can be more efficient. | 2022-04-05 | 3 | IP | 3
4 | As a procrastinator, I would like to be able to visualize my time tracked on the app so I can easily tell how much time I spend off track. | 2022-04-05 | 4 | IP | 6
2 | As a user, I would like the ability to unlock different kinds of trees to increase my motivation to use the app. | 5 | 5 | IP | 3
17 | As a user, I would like push notifications, so that I can be reminded to use the app. | 5 | 6 | W | 3
8 | As a user, I want to be able to export my tracked data to different devices, so that I can view my data easily. | 6 | 7 | W | 5
5 | As someone who struggles to focus, I would like in-app push notifications, so that I may be engaged and reminded to continue using the app. | 7 | 8 | W | 2
9 | As a procrastinator, I want to be able to set goals for myself so that I keep myself motivated. | 7 | 9 | W | 2
11 | As a student, I want to be able to track my schoolwork goals, so that I may be held accountable over time for my busy schedule. | 8 | 10 | W | 3
14 | As a student, I want reminders sent to my phone so that I can remember my due dates. | 8 | 11 | W | 2
3 | As a competitive person, I would like a time based leaderboard in order to compete with my friends. | 9 | 12 | W | 4
10 | As a mother, I want family-friendly options, so that my children are able to use the app to focus on schoolwork. | 9 | 13 | W | 2
12 | As a school-teacher, I want a guest option, so my students can use the app in class to focus on schoolwork. | 10 | 14 | W | 5
6 | As someone with sensitive eyes, I would like dark mode so that I don’t strain my eyes with the typical format. | 11 | 15 | W | 1
15 | As someone who plays mobile games, I want to be able to spend money on this game so that I can progress faster and unlock more mutations. | 11 | 16 | W | 3
16 | As an environmentalist, I want my virtual trees to be converted into real trees so that I can actively help save the environment. | 12 | 17 | W | 5
| Total Story Points |  |  |  | 58