## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
13 | As someone who owns a small business, I want an app that tracks my progress being productive, so I can track and be proactive with a self-set schedule. | 1. Set up the environment in Android Studio 2. Create a mock UI | 1 | Create the environment UI Mockup | F, KA | 4 | 1 | Matthew Brown - 25% Declan Brinn - 25% Caiden Emerson - 25% Sean Staton - 25%
1 | As a professional, I would like calendar functionality so that I may keep my schedule organized. | 1. Learn about adding a calander in Java 2. Create a mock UI | 1 | Knowledge Aquisition UI Mockup | F, KA | 5 | 1 | Matthew Brown - 25% Declan Brinn - 25% Caiden Emerson - 25% Sean Staton - 25%
13 | As someone who owns a small business, I want an app that tracks my progress being productive, so I can track and be proactive with a self-set schedule. | 1. Add the main tab and the functionality to switch to it | 2 | Program the UI and fucntionality | F | 4 | 2 | Matthew Brown - 25% Declan Brinn - 25% Caiden Emerson - 25% Sean Staton - 25%
1 | As a professional, I would like calendar functionality so that I may keep my schedule organized. | 1. Add the calender tab and the functionality to switch to it | 2 | Program the UI | F | 5 | 2 | Matthew Brown - 25% Declan Brinn - 25% Caiden Emerson - 25% Sean Staton - 25%